## Arkusz1
Stage | Sub-task | Persons assigned | start date | end date | Status | November |  | December |  |  |  | January |  |  |  |  | Febuary |  |  |  | March |  |  |  | April |  |  |  | May
[6 empty] | 1 week | 2 week | 3 week | 4 week | 5 week | 6 week | 7 week | 8 week | 9 week | 10 week | 11 week | 12 week | 13 week | 14 week | 15 week | 16 week | 17 week | 18 week | 19 week | 20 week | 21 week | 22 week | 23 week | 24 week
[6 empty] | 2022-11-21 | 2022-11-28 | 2022-12-05 | 2022-12-12 | 2022-12-19 | 2022-12-26 | 2023-01-02 | 2023-01-09 | 2023-01-16 | 2023-01-23 | 2023-01-30 | 2023-02-06 | 2023-02-13 | 2023-02-20 | 2023-02-27 | 2023-03-06 | 2023-03-13 | 2023-03-20 | 2023-03-27 | 2023-04-03 | 2023-04-10 | 2023-04-17 | 2023-04-24 | 2023-05-01
Stage 0 - Preparations | Grease the gears | Sławek | 2022-11-20 | 2022-11-28 | Done
| Plan out the Architecture | Konrad, Mateusz, Sławek | 2022-11-21 | 2022-12-18 | Done
| Brainstorm ideas | Konrad, Mateusz, Sławek | 2022-11-21 | 2022-12-18 | Done
| Install software on raspberry Pi | Sławek, Konrad | 2022-11-21 | 2022-11-29 | Done
| Create Githup repoository for the project | Sławek | 2022-11-29 | 2022-12-18 | Done
Stage 1 - Follow The line | Test Pi Camera with different FOV Lenses | Sławek | 2022-12-18 | 2022-12-24 | Done
| Python class - Detect lines | Sławek | 2022-12-18 | 2023-01-01 | Done
| Python class - Algorithm for lane following | Sławek | 2022-12-18 | 2023-01-01 | Done
| Nucleo - improve comunications with raspberry | Konrad, Mateusz | 2022-12-18 | 2023-01-15 | Done
| Nucleo - read current speed | Konrad, Mateusz | 2022-12-18 | 2023-01-23 | Done
| Implenet ultrasonic detector | Konrad, Mateusz | 2023-01-15 | 2023-01-22 | Done
| Python debuger for PC | Sławek, Mateusz | 2022-12-27 | 2023-02-12 | Done
Stage 2 - Do you wanna build a test track? | Build Test Track - intersections, rundabout, parking , ramp. | Konrad, Mateusz, Sławek | 2023-01-08 | 2023-02-18 | Done
| Build Test track - traffic lights , signs, pedestrian. | Konrad, Mateusz, Sławek | 2023-01-08 | 2023-01-25 | Done
| Improve algorithm for lane following | Sławek | 2023-01-15 | 2023-02-12 | Done
| Python class for GPS handeling and route planning | Sławek | 2023-01-27 | 2023-02-12 | Done
| Python class for Vehicle2Vehicle | Konrad | 2023-01-27 | 2023-02-13 | Done
| Python class for object detection | Mateusz | 2023-01-27 | 2023-02-13 | Done
| Integrade Python Debugger with any changes | Sławek, Mateusz | 2023-02-10 | 2023-02-13 | Done
Stage 3 - desperate maneuvers | Maneuver - parking | Sławek, Konrad | 2023-02-12 | 2023-02-20 | Done
| Maneuver - intersection | Sławek, Konrad | 2023-02-20 | 2023-02-28 | Done
| Maneuver - roundabout | Sławek, Konrad | 2023-02-20 | 2023-02-28 | Done
| Maneuver - that one exit from highway to contry road | Sławek, Konrad | 2023-02-12 | 2023-03-12 | Done
| Maneuver - Overtaking (switch lanes) | Konrad, Sławek | 2023-02-12 | 2023-03-12 | Done
| Integrade Python Debugger with any changes | Sławek, Mateusz | 2023-03-01 | 2023-03-12 | Done
| Prepare for midgate | Sławek, Konrad, Mateusz | 2023-03-06 | 2023-03-12 | Done
Stage 4 - AS loong as it works | GPS talker | Konrad | 2023-03-12 | 2023-04-20 | In Progress
| Vehicle detection | Konrad | 2023-03-12 | 2023-04-20 | In Progress
| Obsticle detection | Sławek, Konrad | 2023-03-12 | 2023-04-26 | In Progress
| Integrade Python Debugger with any changes | Sławek, Mateusz | 2023-04-08 | 2023-04-26 | In Progress
| Test Test Test | Sławek, Mateusz, Konrad | 2023-03-12 | 2023-05-02 | In Progress
Stage 5 - Are we there yet? | Final tests and improvments | Konrad, Sławek, Mateusz | 2023-04-26 | 2023-05-02
| Win the competition | Mateusz, Sławek, Konrad | 2023-05-01 | 2023-05-07